## Slide 1: Project Management for IT ITM 471/571 Closing a Project
Kathy Kotowski
School of Applied Technology
Fall 2016

## Slide 2: Summary of Chapter 8
Getting client acceptance
Installing project deliverables
Conducting the post-implementation audit
Writing the final report
Celebrating success
Ch08: How to Close a TPM Project
Notes: Explain how each of these contributes to the growing importance of project management in the business world.

## Slide 3: Are We There Yet?
The project is done when(choose one):
  You deliver the deliverable and the customer accepts it
  The stakeholders agree to end it
  Never, it will go on forever!
  It fails (and everyone admits it)
  It’s cancelled (due to outside influences)
The ability to accurately assess the state of the project is key

## Slide 4: Ch08: How to Close a Project
Acceptance criteria must be clearly defined
Criteria defined during project planning
Avoid 11th hour disputes
Why Do I Need Client Acceptance Procedures?

## Slide 5: Sample acceptance checklist

## Slide 8: Ch08: How to Close a Project
Installing Project Deliverables
Cut-Over (direct) Approach
Parallel Approach
Phased Approach
By Business Unit Approach

## Slide 9: Installation
After development and testing, system must be put into operation
Important planning considerations
  Costs of operating both systems in parallel
  Detecting and correcting errors in new system
  Potentially disrupting the company and IS operations
  Training personnel and customers with new procedures

## Slide 10: Direct Installation
New system installed and quickly made operational
Overlapping systems turned off
Both systems concurrent for brief time
Advantage – simplicity and fewer logistics issues to manage
Disadvantage – risk due to no backup

## Slide 11: Direct Installation and Cutover

## Slide 12: Parallel Installation
Old and new systems operated together for extended period of time
Advantages – low risk of system failure and continual backup
Disadvantage – cost to operate both systems
  Hiring temporary personnel
  Acquiring extra space
  Increasing managerial and logistical complexity

## Slide 13: Parallel Installation and Operation

## Slide 14: Phased Installation
New system installed in series of steps or phases
Each phase adds components to existing system
Advantage – reduces risk because phase failure is less serious than system failure
Disadvantage – multiple phases cause more activities, milestones, and management complexity for entire effort

## Slide 15: Phased Installation with Direct Cutover and Parallel Operation

## Slide 16: By business-unit Installation
New system installed for certain portions of the company or specified trial locations
Advantages?
Disadvantages?

## Slide 17: Audit (Team project assessment)
Audit goals
  Identify the successes and failures
  Gain an understanding of why (root causes)
  Learn and record the knowledge
The process
  Start with objective actual vs. planned data, then supplement with testimonials
  Identify significant goods and bads
  Do the detective work to determine the true sources
  Record the lessons learned for future improvement

## Slide 18: Keys to an Effective Audit
It’s not about blame
  Chances are it was more process than person anyway
Focus on the big items
  Chances are solving them will probably correct the little ones anyway
Try to balance positives and negatives
  No project is all good or all bad
  You can learn as much from your successes
Get a good scribe

## Slide 19: Questions to Address
Did the team follow the plan?
Was the schedule appropriate? budget?
Did the PM lead effectively? manage?
Was the team cohesive and effective?
Did we have the right people? tools? training?, etc.
Was risk managed well? change?
Was communication proactive?
Were we able to do it right?

## Slide 20: Evaluating Performance
Start with teams, then look at individuals
Gather feedback from multiple sources
Be objective, fact-based, honest and just
Keep true to the accountabilities established during planning
Emphasize successes and areas in need of improvement
Reward those who made it happen

## Slide 21: Ch08: How to Close a Project
Was the project goal achieved?
  Does it do what project team said it would?
  Does it do what client said it would?
Was the project work done on time, within budget, and according to specification?
Was the client satisfied with the project results?
Was business value realized?
  Check success criteria
What lessons were learned about your project management methodology?
How well did the team follow the methodology?
Audit – more questions

## Slide 22: Ch08: How to Close a Project
Managers don’t want to know
Managers don’t want to pay the cost
It’s not a high priority
There’s too much other scheduled work to do
Reasons for not doing a post-implementation audit

## Slide 23: Ch08: How to Close a Project
Reference for future changes in deliverables
Historical record for estimating duration and cost on future projects, activities and tasks
Training resource for new project managers
Input for further training and development of the project team
Input for performance evaluation by the functional managers of the project team members
Documenting the Project

## Slide 24: Ch08: How to Close a Project
POS
Proposal and backup data
Original and revised project schedules
Minutes of all project team meetings
Copies of all status reports
Design documents
Copies of all change notices
Copies of all written communications
Outstanding issues reports
Final report
Sample deliverables (if appropriate)
Client acceptance documents
Post-implementation audit report
Documenting the Project – The Project Notebook

## Slide 25: Ch08: How to Close a Project
Executive Summary
Overall success and performance of project
Organization and administration of project
Techniques used to accomplish results
Strengths and weaknesses of the approach
Recommendations
Appendices
  POS
  WBS
  Resource Schedule
  Change Requests
  Final Deliverables
  Other
Final Project Report (ITM 571: include this in Case studies)

## Slide 26: Where Do We Go From Here?
Celebrate success, or at least the accomplishment of completion
Respect the team’s momentum and comfort with each other
Look for opportunities to advance individuals
Relax, reflect and refresh
Do it again - only this time do it better!