## Sheet1
Round One
| Blue = question | Green = answer
Category/ Points | Intro to PM | Project Scope Management | Planning Process Group | Project Time Management | Miscellaneous
5 | A temporary endeavor undertaken to create a unique product, service, or result | Three components of the Triple Constraint Model | An output of the planning process which details the requirements that must be met | A task which must be completed before another begins is called a ___ task | The number of project knowledge areas, according to the PMBOK
| PROJECT | SCOPE, TIME, COST, QUALITY | RBS | PREDECESSOR | TEN
10 | The number of process groups in a project management methodology | Name two tools or techniques for collecting project requirements | An output of the planning process which details the activities and tasks needed to create the requirements | _____ is the amount of time an activity can be delayed from its early start without delaying the planned project finish date | What is the first process in planning a project schedule - defining milestones, activities, or requirements?
| FIVE | INTERVIEWS FOCUS GROUPS SURVEYS GUIDED GROUP SESSIONS OBSERVATIONS | WBS chart | SLACK | REQUIREMENTS
15 | Initial cost estimates are performed within this process group | The tendency for the list of project requirements to keep growing is called: | You cannot clean the kitchen counter until all of the dirty dishes have been put in the dishwasher. What type of task dependency is this? | Adding additional resources to a task in order to shorten the schedule is called: | Which pass through a project network diagram determines the late start and late finish dates for each activity?
| INITIATING | SCOPE CREEP | Finish to start FS | CRASHING | BACKWARD OR SECOND
20 | This process measures progress toward project objectives and takes corrective actions | The process of having stakeholders verify the list of requirements for a project | A product or service produced as part of a project | A method used to determine the project schedule which includes determining early and late start and finish dates | A project with team members in Chicago, London, and Mumbai is an example of a:
| MONITORING & CONTROLLING | SCOPE VALIDATION | DELIVERABLE | PRECEDENCE DIAGRAMMING METHOD | VIRTUAL TEAM
Round Two | Intro to PM | Estimating Techniques | Planning Process Group | Risk Management | Project Cost Management
10 | Who has the authority to approve changes to the project scope, schedule, or budget? | The series of tasks that determine the earliest time by which a project can be completed. | This software produced by Microsoft automates the planning and monitoring processes of Project Management | Driving a different route to school in case of bad traffic on your regular route is an example of what type of risk response? | The salary paid to a team member for work directly related to the project is a ___ cost.
| PROJECT SPONSOR | CRITICAL PATH | MS PROJECT | AVOIDANCE | TANGIBLE OR DIRECT
20 | Detailed estimates of the work to be done are developed in which process group? | Assigning durations (or costs) to each low-level task on the WBS chart is __ estimation | This chart depicts tasks and dependencies in a horizontal bar-chart format. | Determining the likelihood and impact of potential future events are parts of this step within Risk Mgmt.: | Which type of cost estimate is performed after the team has completed the requirements gathering activities?
| PLANNING | BOTTOM-UP | GANTT CHART | RISK ASSESSMENT | BUDGETARY ESTIMATE
30 | Having some project tasks performed by people who live in a different country, especially overseas is an example of: | A painter who estimates the cost of a paint job based upon the number of windows as well as the height and width of walls is using this type of estimating technique. | A black diamond on a Gantt chart represents this. | Reducing the probability OR the impact of a risk is known as risk : | Estimating both the costs of creating new software as well as supporting that software in a production environment for 5 years is an example of:
| OFFSHORING | PARAMETRIC | MILESTONE | MITIGATION | LIFE CYCLE COSTING
40 | Which organizational structure has both Project Managers and Functional Managers overseeing employees? | Which cost estimation technique might be best for a project that is VERY SIMILAR to recently completed projects? | What are three main outputs of the Planning Process Group? | What is involved in risk quantitative analysis? | Money set aside to cover unknown emergencies might be a type of:
| MATRIX | ANALOGOUS | WBS (Scope), Budget (Cost), Schedule (Time) | Assessing both the probability and the impact of a risk event | MANAGEMENT RESERVES
Bonus Question | Name 3 of the 5 risk responses |  |  | ACCEPTANCE, AVOIDANCE, CONTINGENCY PLANNING, MITIGATION, TRANSFERENCE