## Slide 1: Project Management for IT ITMM 471 ITMM 571
Kathy Kotowski
Spring 2017

## Slide 2
Team Project Guidelines

## Slide 3: Assignment Overview
Develop, implement and assess a project plan to conduct an online instructional video or webinar
  You choose the topic/purpose
  You develop and produce the video
Deliverables
  Team contract (2/1/2017)
  Progress report 1 (2/19/2017)
  Progress report 2 (3/19/2017)
  The webinar (4/2/2017)
  Assessments of your project’s success (4/16/2017)

## Slide 4: Team Contract/Charter
Choose a webinar/video topic
Identify the roles and responsibilities of each team member
Choose team leads:
  Team charter
  Progress report 1
  Progress report 2
  Final publication
  MS Project Admin
  Project metrics analyst
Establish method and frequency of team communication
  Google hangouts or ??
  In-person meetings

## Slide 5: Earned Value Management
Track the actual time and cost as you execute your plan – use MS Project
Complete your EVM graph by plotting the actual time and cost needed to achieve each milestone
This will be critical evidence for your final assessment
Describe and capture any other metrics you feel are necessary to prove project success

## Slide 6: The Project Plan
Before doing anything else, document your plan!!!!
  Describe the webinar
  Identify the activities (WBS)
  Diagram the precedence relationships
  Estimate the budget
    Remember to include labor costs
  State the deliverables and desired quality
  Document your risk management plan
  Build the schedule including milestones
    document the planned time and earned value at each milestone and use to create an Earned Value graph

## Slide 7: Team Assessment
Append 2 pages to your plan document
Page 1 – Earned Value Management
  A single EVM graph (original PV line plus EV and AC lines)
Page 2 – Supporting metrics
  1 table of data (duration and cost at each milestone)
  1 table of metrics (SV, CV, SPI, and CPI at each milestone)

## Slide 8: Individual Assessment
Each student will submit a project audit
Analysis
  Explain the results of each milestone
  Explain improvements you would make next time
Key findings
Improvement opportunities

## Slide 9: Important Notes
You are not being graded on the accuracy of your plan, but rather on your ability to build, execute and objectively assess it
  It is expected that there will be discrepancies
  Be honest in your data collection and assessments
Remember that this assignment has 3 distinct parts (plan, execute, assess)

## Slide 10
Project Teams:
ITMM 471
Notes: This is another option for an Overview slides using transitions.

## Slide 11: Team A
Team members
  Jose “Chief”
  Carlos
  Guzel
  Osman
  Jarron
  David P

## Slide 12: Team B
Team members
  Davon
  Erin
  Christian
  Ian
  Ken E
  Amairani

## Slide 13: Team C
Team members
  Blake
  Shan
  Sarina
  Mathias
  Scott
  Zachary

## Slide 14: Team D
Team members
  Joshua
  Abigail
  Timothy
  Ramzee
  Bobby
  Jacob

## Slide 15: Team E
Team members
  Jorell
  Irshad
  David D
  Fahad
  Henry
  Chris

## Slide 16: Team F
Team members
  Andrew
  Kenneth Y
  Devonald
  Bhumi
  Eli
  Tom

## Slide 17: Team G
Team members
  Olu
  Matt
  Dennis
  Jingwen
  Peter
  Zabe

## Slide 18: Team H (online)
Team members
  Mohmedamir
  Danalee
  Marika
  April
  Mohammed
  Daniel

## Slide 19
Project Teams:
ITMM 571
Notes: This is another option for an Overview slides using transitions.

## Slide 20: Team A
Team members
  Maria
  Sri Haritha
  Jayanth
  Sri
  Sabarathinam

## Slide 21: Team B
Team members
  Pritesh
  Sarin
  Arjun
  Vipal
  Abhishek
  Rakini

## Slide 22: Team C
Team members
  Ankini
  Neha
  Shravan
  Thamizharasan
  Sharan
  Nicholas

## Slide 23: Team D
Team members
  Poornima
  Smita
  Yash
  Sumit
  Anirudh
  Shakshi

## Slide 24: Team E - online
Team members
  Rakshith
  Aditya
  Priyanka
  Sohail
  Poonam

## Slide 25: Team F - online
Team members
  Dhara
  Amit
  Niti
  Gururaj

## Slide 26: Team G - online
Team members
  Dinesh
  Gurjot
  Suman
  Ivan
  Ramanuja