## Slide 1: Chapter 11: Project Risk Management
Information Technology Project Management, Eighth Edition

## Slide 2: The Importance of Project Risk Management
Project risk management is the art and science of identifying, analyzing, and responding to risk throughout the life of a project and in the best interests of meeting project objectives
Risk management is often overlooked in projects, but it can help improve project success by helping select good projects, determining project scope, and developing realistic estimates

## Slide 3: Figure 11-1. Benefits from Software Risk Management Practices*
*Source: Kulik and Weber, KLCI Research Group

## Slide 4: Negative Risk
A dictionary definition of risk is “the possibility of loss or injury”
Negative risk involves understanding potential problems that might occur in the project and how they might impede project success
Negative risk management is like a form of insurance; it is an investment

## Slide 5: Risk Can Be Positive
Positive risks are risks that result in good things happening; sometimes called opportunities
A general definition of project risk is an uncertainty that can have a negative or positive effect on meeting project objectives
The goal of project risk management is to minimize potential negative risks while maximizing potential positive risks

## Slide 6: Project Risk Management Processes
Planning risk management : Deciding how to approach and plan the risk management activities for the project
Identifying risks: Determining which risks are likely to affect a project and documenting the characteristics of each
Performing qualitative risk analysis: Prioritizing risks based on their probability and impact of occurrence

## Slide 7: Project Risk Management Processes (cont’d)
Performing quantitative risk analysis: Numerically estimating the effects of risks on project objectives
Planning risk responses: Taking steps to enhance opportunities and reduce threats to meeting project objectives
Controlling risk: Monitoring identified and residual risks, identifying new risks, carrying out risk response plans, and evaluating the effectiveness of risk strategies throughout the life of the project

## Slide 8: Planning Risk Management
The main output of this process is a risk management plan—a plan that documents the procedures for managing risk throughout a project
The project team should review project documents and understand the organization’s and the sponsor’s approaches to risk
The level of detail will vary with the needs of the project

## Slide 9: Table 11-2. Topics Addressed in a Risk Management Plan
Methodology
Roles and responsibilities
Budget and schedule
Risk categories
Risk probability and impact
Revised stakeholders’ tolerances
Tracking
Risk documentation

## Slide 10: Contingency and Fallback Plans, Contingency Reserves
Contingency plans are predefined actions that the project team will take if an identified risk event occurs
Fallback plans are developed for risks that have a high impact on meeting project objectives, and are put into effect if attempts to reduce the risk are not effective
Contingency reserves or allowances are provisions held by the project sponsor or organization to reduce the risk of cost or schedule overruns to an acceptable level; management reserves are funds held for unknown risks that are NOT part of the cost baseline but ARE part of the budget and funding requirements

## Slide 11: Broad Categories of Risk
Market risk
Financial risk
Technology risk
People risk
Structure/process risk

## Slide 12: Risk Breakdown Structure
A risk breakdown structure is a hierarchy of potential risk categories for a project
Similar to a work breakdown structure but used to identify and categorize risks

## Slide 13: Figure 11-4. Sample Risk Breakdown Structure

## Slide 14: Table 11-4. Potential Negative Risk Conditions Associated With Each Knowledge Area

## Slide 15: Identifying Risks
Identifying risks is the process of understanding what potential events might hurt or enhance a particular project
Another consideration is the likelihood of advanced discovery
Risk identification tools and techniques include:
  Brainstorming
  The Delphi Technique
  Interviewing
  SWOT analysis
Use published checklists
www.projectoffice.gr/Risk%20Management%20Checklist.doc
Review past projects “post mortems”

## Slide 16: Brainstorming
Brainstorming is a technique by which a group attempts to generate ideas or find a solution for a specific problem by amassing ideas spontaneously and without judgment
An experienced facilitator should run the brainstorming session
Be careful not to overuse or misuse brainstorming.
  Psychology literature shows that individuals produce a greater number of ideas working alone than they do through brainstorming in small, face-to-face groups
  Group effects often inhibit idea generation

## Slide 17: Delphi Technique
The Delphi Technique is used to derive a consensus among a panel of experts who make predictions about future developments
Provides independent and anonymous input regarding future events
Uses repeated rounds of questioning and written responses and avoids the biasing effects possible in oral methods, such as brainstorming

## Slide 18: Interviewing
Interviewing is a fact-finding technique for collecting information in face-to-face, phone, e-mail, or instant-messaging discussions
Interviewing people with similar project experience is an important tool for identifying potential risks

## Slide 19: SWOT Analysis
SWOT analysis (strengths, weaknesses, opportunities, and threats) can also be used during risk identification
Helps identify the broad negative and positive risks that apply to a project

## Slide 21
Risk Identification Matrix Template
RISK CATEGORIES AND RISKS | SCOPE TRIANGLE ELEMENTS |  |  |  | 
 | Scope | Time | Cost | Quality | Resources
Technical |  |  |  |  | 
Project Management |  |  |  |  | 
Organizational |  |  |  |  | 
External |  |  |  |  | 

## Slide 22: Risk Register
The main output of the risk identification process is a list of identified risks and other information needed to begin creating a risk register
A risk register is:
  A document that contains the results of various risk management processes and that is often displayed in a table or spreadsheet format
  A tool for documenting potential risk events and related information
Risk events refer to specific, uncertain events that may occur to the detriment or enhancement of the project

## Slide 23: Table 11-5. Sample Risk Register
• No.: R44
• Rank: 1
• Risk: New customer
• Description: We have never done a project for this organization before and don’t know too much about them. One of our company’s strengths is building good customer relationships, which often leads to further projects with that customer. We might have trouble working with this customer because they are new to us.
• Category: People risk
• Etc.

## Slide 24
Risk Log Entry
ID #
Risk Description
Risk Owner
Action to be Taken
Outcome
P
I

## Slide 25: Performing Qualitative Risk Analysis
Assess the likelihood and impact of identified risks to determine their magnitude and priority
Risk quantification tools and techniques include:
  Probability/impact matrixes
  The Top Ten Risk Item Tracking
  Expert judgment

## Slide 26: Probability/Impact Matrix
A probability/impact matrix or chart lists the relative probability of a risk occurring on one side of a matrix or axis on a chart and the relative impact of the risk occurring on the other
List the risks and then label each one as high, medium, or low in terms of its probability of occurrence and its impact if it did occur
Can also calculate risk factors:
  Numbers that represent the overall risk of specific events based on their probability of occurring and the consequences to the project if they do occur

## Slide 27: Figure 11-5. Sample Probability/Impact Matrix

## Slide 28
Static Risk Assessment Matrix - Qualitative
Figure
03-03
Ch03: What Are the PM Process Groups?

## Slide 29: Watch List
A watch list is a list of risks that are low priority, but are still identified as potential risks
Qualitative analysis can also identify risks that should be evaluated on a quantitative basis

## Slide 30: Performing Quantitative Risk Analysis
Often follows qualitative risk analysis, but both can be done together
Large, complex projects involving leading edge technologies often require extensive quantitative risk analysis
Main techniques include:
  Decision tree analysis
  Simulation
  Sensitivity analysis

## Slide 31: Decision Trees and Expected Monetary Value (EMV)
A decision tree is a diagramming analysis technique used to help select the best course of action in situations in which future outcomes are uncertain
Estimated monetary value (EMV) is the product of a risk event probability and the risk event’s monetary value
You can draw a decision tree to help find the EMV

## Slide 32: Figure 11-7. Expected Monetary Value (EMV) Example

## Slide 33: Simulation
Simulation uses a representation or model of a system to analyze the expected behavior or performance of the system
Monte Carlo analysis simulates a model’s outcome many times to provide a statistical distribution of the calculated results
To use a Monte Carlo simulation, you must have three estimates (most likely, pessimistic, and optimistic) plus an estimate of the likelihood of the estimate being between the most likely and optimistic values

## Slide 34: Figure 11-8. Sample Monte Carlo Simulation Results for Project Schedule

## Slide 35: Planning Risk Responses
After identifying and quantifying risks, you must decide how to respond to them
Four main response strategies for negative risks:
  Risk avoidance
  Risk acceptance
  Risk transference
  Risk mitigation
Four main response strategies for positive risks:
  Risk exploitation
  Risk sharing
  Risk enhancement
  Risk acceptance

## Slide 36: Table 11-7. General Risk Mitigation Strategies for Technical, Cost, and Schedule Risks

## Slide 37: Residual and Secondary Risks
It’s also important to identify residual and secondary risks
Residual risks are risks that remain after all of the response strategies have been implemented
Secondary risks are a direct result of implementing a risk response

## Slide 38: Controlling Risks
Involves executing the risk management process to respond to risk events and ensuring that risk awareness is an ongoing activity performed by the entire project team throughout the entire project
Workarounds are unplanned responses to risk events that must be done when there are no contingency plans
Main outputs of risk control are:
  Work performance information
  change requests
  updates to the project management plan, other project documents, and organizational process assets

## Slide 39: Chapter Summary
Project risk management is the art and science of identifying, analyzing, and responding to risk throughout the life of a project and in the best interests of meeting project objectives
Main processes include:
  Plan risk management
  Identify risks
  Perform qualitative risk analysis
  Perform quantitative risk analysis
  Plan risk responses
  Control risks