## Slide 1: Chapter 7: Project Cost Management
Information Technology Project Management, Eighth Edition

## Slide 2: Learning Objectives
Understand the importance of project cost management
Explain basic project cost management principles, concepts, and terms
Describe the process of planning cost management
Discuss different types of cost estimates and methods for preparing them

## Slide 3: Learning Objectives
Understand the processes of determining a budget and preparing a cost estimate for an information technology (IT) project
Understand the benefits of earned value management and project portfolio management to assist in cost control
Describe how project management software can assist in project cost management

## Slide 4: The Importance of Project Cost Management
IT projects have a poor track record for meeting budget goals
A cost overrun is the additional percentage or dollar amount by which actual costs exceed estimates
A 2011 Harvard Business Review study reported an average cost overrun of 27 percent. The most important finding was the discovery of a large number of gigantic overages or “black swans”

## Slide 5: What Went Wrong?
The United Kingdom’s National Health Service IT modernization program was called the greatest IT disaster in history with an estimated $26 billion overrun
The program had problems due to incompatible systems, resistance from physicians, and arguments among contractors about who’s responsible for what
It was finally scrapped in 2011

## Slide 6: What is Cost and Project Cost Management?
Cost is a resource sacrificed or foregone to achieve a specific objective or something given up in exchange
Costs are usually measured in monetary units like dollars
Project cost management includes the processes required to ensure that the project is completed within an approved budget

## Slide 7: Project Cost Management Processes
Planning cost management :determining the policies, procedures, and documentation that will be used for planning, executing, and controlling project cost.
Estimating costs: developing an approximation or estimate of the costs of the resources needed to complete a project
Determining the budget: allocating the overall cost estimate to individual work items to establish a baseline for measuring performance
Controlling costs: controlling changes to the project budget

## Slide 8: Basic Principles of Cost Management
Most members of an executive board better understand and are more interested in financial terms than IT terms , so IT project managers must speak their language
  Profits are revenues minus expenditures
  Profit margin is the ratio of revenues to profits
  Life cycle costing considers the total cost of ownership, or development plus support costs, for a project
  Cash flow analysis determines the estimated annual costs and benefits for a project and the resulting annual cash flow

## Slide 9: Media Snapshot
You cannot measure ROI unless you have a benefits measurement process in place
A 2015 report by PMI found:
  Only 20 percent of organizations report having a high level of benefits realization maturity
  39 percent of high-performing organizations report high benefits realization maturity compared to 9 percent of low performers

## Slide 10: Types of Costs and Benefits
Tangible costs or benefits are those costs or benefits that an organization can easily measure in dollars
Intangible costs or benefits are costs or benefits that are difficult to measure in monetary terms
Direct costs are costs that can be directly related to producing the products and services of the project
Indirect costs are costs that are not directly related to the products or services of the project, but are indirectly related to performing the project
Sunk cost is money that has been spent in the past; when deciding what projects to invest in or continue, you should not include sunk costs

## Slide 11: More Basic Principles of Cost Management
Learning curve theory states that when many items are produced repetitively, the unit cost of those items decreases in a regular pattern as more units are produced
Reserves are dollars included in a cost estimate to mitigate cost risk by allowing for future situations that are difficult to predict
  Contingency reserves allow for future situations that may be partially planned for (sometimes called known unknowns) and are included in the project cost baseline
  Management reserves allow for future situations that are unpredictable (sometimes called unknown unknowns

## Slide 12: Planning Cost Management
The project team uses expert judgment, analytical techniques, and meetings to develop the cost management plan
A cost management plan includes:
  Level of accuracy and units of measure
  Organizational procedure links
  Control thresholds
  Rules of performance measurement
  Reporting formats
  Process descriptions

## Slide 13: Estimating Costs
Project managers must take cost estimates seriously if they want to complete projects within budget constraints
It’s important to know the types of cost estimates, how to prepare cost estimates, and typical problems associated with IT cost estimates

## Slide 14: Table 7-1. Types of Cost Estimates

## Slide 15: More on Cost Estimates
The number and type of cost estimates vary by application area. The Association for the Advancement of Cost Engineering International identifies five types of cost estimates for construction projects: order of magnitude, conceptual, preliminary, definitive, and control
Estimates are usually done at various stages of a project and should become more accurate as time progresses
A large percentage of total project costs are often labor costs

## Slide 16: Table 7-2. Maximum FTE by Department by Year

## Slide 17: Cost Estimation Tools and Techniques
Basic tools and techniques for cost estimates:
  Analogous or top-down estimates: use the actual cost of a previous, similar project as the basis for estimating the cost of the current project
  Bottom-up estimates: involve estimating individual work items or activities and summing them to get a project total
  Parametric modeling uses project characteristics (parameters) in a mathematical model to estimate project costs

## Slide 18: Typical Problems with IT Cost Estimates
Estimates are done too quickly
People lack estimating experience
Human beings are biased toward underestimation
Management desires accuracy

## Slide 19: Sample Cost Estimate
See the text for a detailed example of creating a cost estimate for the Surveyor Pro project described in the opening case
Before creating an estimate, know what it will be used for, gather as much information as possible, and clarify the ground rules and assumptions for the estimate
If possible, estimate costs by major WBS categories
Create a cost model to make it easy to make changes to and document the estimate

## Slide 20: Figure 7-2. Surveyor Pro Project Cost Estimate

## Slide 21: Figure 7-3. Surveyor Pro Software Development Estimate

## Slide 22: Best Practice
Alvin Alexander wrote a book called Cost Estimating in an Agile Development Environment in 2015
Function points are a means of measuring software size in terms that are meaningful to end users
User stories are a common way to describe requirements in a simple, concise way
Developers can analyze user stories to estimate function points and person-hours

## Slide 23: Determining the Budget
Cost budgeting involves allocating the project cost estimate to individual work items over time
The WBS is a required input to the cost budgeting process since it defines the work items
Important goal is to produce a cost baseline
  a time-phased budget that project managers use to measure and monitor cost performance

## Slide 24: Figure 7-4. Surveyor Pro Project Cost Baseline